## Slide 1
<number>
Project General Assembly Meeting
24 August 2018 – Joensuu (FI)
F2F Meeting
WP3: Open Data and e-Infrastructures
P11- CASC4DE
24/08/2018

## Slide 2
WP3 – Open Data and e-Infrastructure - CASC4DE
WP Timeline
2
Task 3.2 – Data storage and data access – CASC4DE
Task 3.3 - Virtualization of instrument access – CNRS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Task 3.4 – Data processing and data mining – CASC4DE
Task 3.1 – Providing a data management plan for the research infrastructure –CASC4DE
24/08/2018

## Slide 3
Results over the last 3 months at WP level: First version of Data Management Plan is delivered, the content will be discuss in Joensuu. We are Currently working on a web interface to allow users to enter their metadata. A model is shown in Joensuu. We are facing an issue with Strasbourg University staff to access the EU network; we hope to find a solution in September.
WP Progress
<number>
Work package nr | 1 |  |  |  | Partner responsible for the WP |  |  |  |  | CASC4DE |  | 
Work package title | Open Data and e-Infrastructure |  |  |  |  |  |  |  |  |  |  | 
Activity start month and year | 01 2018 |  |  |  |  |  | Activity end month and year |  | 12 2021 |  |  | 
Partners involved | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 11 | 12
Organization acronym | CNRS | LIEG | PRAG | UHRO | UEF | ROMA | FC-LISB | MOSC | WARW |  | CASC4DE | AK
24/08/2018

## Slide 4
Side Technical Meetings Global progress of the WP: 15% Good advancement with respect to the planning
WP Progress
<number>
24/08/2018
Date | Place | Partner | Purpose
19-25/08/18 | Joensuu | All | Validate DMP and metadata format

## Slide 5
Task 3.1: Providing a data management plan for the research infrastructure. From M1 to M48 Task leader: CASC4DE - Participants: All Results vs task scheduling: - First Version Delivered - OnGoing Validation
Task Progress
<number>
24/08/2018

## Slide 6
Problems encountered and risks for the project: Indicate here inconsistencies or deviations from task planning and related risk for the project Planned actions for the next months
Task Progress
<number>
WHO | WHAT | HOW | WHEN
all participants | return exp on DMP | short reports | any time
24/08/2018

## Slide 7
Task 3.2: Data storage and data access. From M6 to M24 Task leader: CASC4DE - Participants: CNRS-LILL, CNRS-ORSA, WARW Results vs task scheduling: We are working on web interfaces to handle the data and metadata produced by EU FT-ICR MS partners. The tool for data access and data sharing has been already chosen (OpenData) and some test have been run. Our current focus is on the metadata : what format should they have and how to produce and share them among the EU FT-ICR MS collaborators in a safe and efficient way. Regarding data storage, we currently have an issue with Strasbourg University staff to have access to the European network to share data with foreigner labs. We are working on it.
Task Progress
<number>
24/08/2018

## Slide 8
Problems encountered and risks for the project: Issue with University staff to access the European network. Planned actions for the next months
Task Progress
<number>
WHO | WHAT | HOW | WHEN
CASC4DE | Find a way to access the EU network | Change of negotiator | September 2018
Other partners | Buy furnitures for data storage in their own lab | Provide a shopping list | M12 2018
24/08/2018

## Slide 9
Task 3.3: Virtualization of instrument access. From M12 to M36 Task leader: CNRS-ORSA - Participants: CNRS-LILL, WARW, CASC4DE Results vs task scheduling: Not started yet
Task Progress
<number>
24/08/2018

## Slide 10
Problems encountered and risks for the project: Indicate here inconsistencies or deviations from task planning and related risk for the project Planned actions for the next months
Task Progress
<number>
WHO | WHAT | HOW | WHEN
24/08/2018

## Slide 11
Task 3.4: Data processing and data mining. From month M24 to M48 Task leader: CASC4DE - Participants: CNRS-ORSA, WARW, CNRS-LILL Results vs task scheduling: Web interface for data processing has been designed and tested. It will improved in the future to be usable by all EU FT-ICR MS collaborators. A new ESR collaborator will hired at CASC4DE to work on data mining.
Task Progress
<number>
24/08/2018

## Slide 12
Problems encountered and risks for the project: Planned actions for the next months
Task Progress
<number>
WHO | WHAT | HOW | WHEN
CASC4DE | data mining | New collaborator | Starting in October 2018
24/08/2018

## Slide 13
<number>
Del. Nr | Title | Leader | Due date ( Month) | Progress / issues
D3.1 | Data management plan | 11 - CASC4DE | 6 | 100 %
D3.2 | Data/metadata specification | 11 - CASC4DE | 12 | 75 %
D3.3 | Users guidelines on the data storage and data access | 11 - CASC4DE | 24 | 15 %
D3.4 | Common interface for remote control of the different FT#ICR spectrometer | 11 - CASC4DE | 24 | 0 %
Deliverables Status
24/08/2018

## Slide 14
<number>
Del. Nr | Title | Leader | Due date ( Month) | Progress / issues
D3.5 | Specific processing, analysis and mining tools for the data processing | 11 - CASC4DE | 48 | 15 %
Deliverables Status
24/08/2018

## Slide 15
<number>
MS no. | Milestone name | WP no. | Leader | Due date | Means of Verifications | Status | Expected date of achievement
MS4 | Data management plan in concertation with all sites and following H2020 recommendations. | 3 | 11 - CASC4DE | 48 | Data management plan in concertation with all sites and following H2020 recommendations. means of verification: Agreement on a data management plan. |  | 
MS5 | Suited common interface with the different FT#ICR spectrometer | 3 | 11 - CASC4DE | 36 | Suited common interface with the different FT#ICR spectrometer. Means of verification: Success of a complete remote acquisition and processing |  | 
Milestone Status
24/08/2018